# Learning and Adaptation through Sentinel sites to demonstrate Integrated service delivery implementation in Uganda

## Background

The MOH has defined a new strategic direction to strengthen and consolidate the integrated delivery of health services. This is in line with the Essential Health Care Package and the National Development Plan 4, and is intended to lead to improved quality, efficiency, and client satisfaction. Uganda is on an accelerated transition from vertical service delivery arrangements to integrated, patient-centered approaches. A National Integration Framework has been developed to guide this process, and initial country guidelines have supported facilities to initiate integration efforts. Recent supervision has demonstrated varying levels of integration but also revealed significant variability in operationalization across districts, levels of care, and regions. To address this variability, MoH proposes to institutionalize a network of Sentinel Learning Sites, structured as practical hubs for demonstrating integrated care, facilitating hands-on learning, and serving as an engine for continuous improvement and operational problem-solving. Sentinel sites will allow regions to move beyond episodic supervision towards a consistent practice of learning, adaptation and dissemination of best practices. This approach aligns with modern Learning Health System models and is consistent with Uganda's strategic ambition for Universal Health Coverage, increased efficiency, and improved patient experience.

### Questions

- What minimum support package (training, tools, mentorship frequency) does each health system level need to successfully integrate health services?

- What specific changes improve service quality and patient outcomes at each level of care?

- What practical interventions can be replicated to standardize comprehensive integrated service delivery in Uganda?

### Objectives

- To improve the quality of integrated service delivery in Uganda through instituting practical interventions that address gaps in processes and systems at levels of care.

- To functionalize shared learning on implementation of integrated health service delivery through replicable adaptations from the sentinel sites to other facilities.

### Theory of Change

If a balanced set of sentinel sites are chosen and provided a structured package of continuous quality-based support and mentorship, process and system inputs, then sentinel sites will become demonstration facilities that generate actionable learning, and support peer-to-peer spread, reducing variability nationally and improving patient experience and service efficiency over time.

## Methods

### Design

A prospective, mixed-methods learning and improvement design over 12 months (March 2026–Feb 2027)

### Sampling

The selection of integration sentinel sites is guided by the principle that sentinel units should be representative, feasible, stable, and capable of generating data that can be generalized beyond the immediate site (WHO, 2012; Bisset et al., 2014). Drawing on the WHO framework for sentinel site selection — which emphasises representativeness, geographic distribution, operational feasibility, and institutional stability — as well as the Learning Health Systems literature that underscores the value of sites embedded within routine systems for generating actionable learning (Witter et al., 2025; Gilson et al., 2020), the identification of integration sentinels will follow a structured, multi-stage process described below.

- Stage 1 — Stratified eligible pool construction. All health facilities across the 16 health zones are stratified by level of care (RRH, District Hospital, PNFP Hospital, HC IV, HC III) and by ownership (Government of Uganda, PNFP, Private-for-Profit). Stratification by level and ownership type is consistent with WHO sentinel site selection guidance which requires that sites represent the diversity of health service delivery arrangements within the system under study (WHO, 2012; Bisset et al., 2014). This produces a sampling frame of five strata per zone, yielding a national pool of 80 potential sentinel positions across 16 zones.

- Stage 2 — Eligibility screening using a standardized checklist. Within each stratum, all facilities are screened against the eligibility criteria set out below. Only facilities meeting all criteria proceed to Stage 3. This approach mirrors the multi-attribute checklist methodology applied in the WHO-guided hospital sentinel site selection process in Indonesia (Bisset et al., 2014), which first shortlisted facilities on performance history before applying detailed criteria. The use of prior supervision data as a screening tool is also consistent with the Learning Health Systems principle that sentinel sites should already exhibit a minimum baseline of systemic function, since poorly performing sites generate low-quality learning signals and risk discrediting the broader programme (Witter et al., 2025).

- Stage 3 — Performance-informed selection within strata. Among eligible facilities in each stratum, facilities are ranked by their average composite integration score from the most recent support supervision round. Facilities scoring 60% or above are included in the selection pool. One facility per stratum per zone is then selected using stratified random sampling (lottery method) from this performance-verified pool. Restricting selection to above-threshold performers ensures a minimum capacity for demonstrating integrated care while random selection within the pool avoids systematic bias toward the highest performers alone — which would undermine the representativeness and generalisability of lessons learned (Guillot et al., 2022; Palinkas et al., 2015). The resulting selection of 80 sites (5 per zone x 16 zones) is listed in Annex I.

- Stage 4 — Stakeholder validation and consent. Selected facilities are presented to district health management teams (DHMTs) and RRH ICS teams for review. Facility in-charges are consulted to confirm willingness and leadership commitment to participate. The WHO sentinel site framework emphasises that institutional motivation and staff willingness are prerequisites for system sustainability (WHO, 2012), and learning site literature across sub-Saharan Africa confirms that sites without genuine leadership buy-in generate fragile learning environments that collapse once external support is withdrawn (Gilson et al., 2020; Witter et al., 2025). Confirmed sites proceed to activation. Substitution of any declined site follows the same Stage 3 ranking within the relevant stratum. See Annex I for the final list of integration sentinels.

Eligibility criteria

Eligibility criteria are operationalized as a standardized checklist applied during Stage 2 screening. The criteria draw on the four core WHO sentinel site attributes (representativeness, feasibility, stability, and data capacity) and on the learning site literature’s emphasis on institutional readiness and leadership commitment (Bisset et al., 2014; Witter et al., 2025).

- Basic functionality: adequate staffing, essential commodities available, functional data systems

- Willingness to test new approaches and document results

- Leadership commitment to participate in monthly learning activities

### Approach

(1) Site activation: site visits

- Agree roles, expectations, and escalation pathways: define who provides mentorship, who leads implementation at the facility, who documents learning, and who escalates constraints, routine reporting, e.t.c

- Validate baseline findings from the support supervision findings and conduct an in-depth analysis understand their integration strategies, challenges, successes.

- Co-develop rolling 3-month operational plans: translate identified gaps into a short-cycle plan with prioritized activities, timelines, responsible persons, required resources, and follow-up actions to track completion and outcomes.

(2) Activities to improve the quality of integrated service delivery in Uganda through instituting practical interventions that address gaps in processes and systems at levels of care.

- Conduct joint supportive supervision

- Conduct joint district/RRH/MoH support visits

- Check tracer enablers: priority commodities/services, key stock tracers, referral/linkages, service-point readiness

- Conduct a structured CQI-based mentorship process to test changes and improvements

- Monthly/Quarterly CQI mentorship/coaching with action plans and follow-up

- Pilot 2–3 high-impact changes per site (one-stop points, task-shifting, integrated appointments)

- Document results and submit monthly learning logs

- Continuously monitor key indicators

- Track integration outcomes and quality routinely via DHIS2 + facility data

- Periodic ad hoc systems checks on enablers (digitization, HRH, supply chain, financing, infrastructure, data use)

- Support practical inputs needed to improve system performance

- Provide/Update/disseminate integration SOPs and job aids

- Provide/strengthen chronic care registers and reporting tools

- Support biometrics/unique ID workflows where applicable

- Use Regional ICS engagements to escalate and unblock system issues

(3) Activities to functionalize shared learning on implementation of integrated health service delivery through replicable adaptations from the sentinel sites to other facilities.

- Hold learning sessions and harvest meetings to enable learning and adaptation - peer-learning exchanges, documentation support, and routine monitoring of agreed indicators.

- Peer-learning exchanges via Regional ICS forums to troubleshoot bottlenecks and share tested fixes

- Harvest results from CQI tests (what changed + effect on wait times, service completion, continuity of care)

- Disseminate findings to other sites through quarterly regional learning sessions, written briefs, and facility exchange visits, brief case stories, etc

- Routine monitoring review using DHIS2 + facility data and tracer indicators (stock/status, referral/linkages, service-point readiness)

- Develop change packages that will be disseminated

- Compile “what works” change bundles works and why in simple, step-by-step formats that other facilities can replicate

- Support other sites to adopt successful strategies with tailored implementation support based on their context

### Data Collection

Data will be collected through three complementary channels: (i) a structured sentinel site data collection form used at activation and at each follow-on visit; (ii) routine DHIS2/HMIS data extraction for agreed performance indicators; and (iii) brief client satisfaction assessments conducted during site visits. This triangulated approach aligns with best practice in learning health systems, where combining primary field data with routine system data enables both real-time operational learning and trend monitoring over time (Witter et al., 2025).

Sentinel Site Data Collection Form. A single, standardized data collection form (see Annex II) is used at two points: (a) at activation, to establish a validated baseline and agree operational expectations; and (b) at each follow-on supervisory visit, to track progress against the baseline and document CQI cycle outcomes. The form is structured in three modules: Site Profile and Readiness (completed once at activation); Visit Record and Action Tracker (completed at each follow-on visit); and Learning and Adaptation Log (completed at each visit). The form is designed to be completed within 60 minutes, minimizing burden on facility staff in line with WHO recommendations that sentinel data collection instruments should be simple and not overstretch routine workforce capacity (WHO, 2012).

Routine DHIS2/HMIS data. Agreed priority indicators (see Table 1) are abstracted monthly from DHIS2 and facility registers by the regional ICS team. These provide the quantitative performance backbone of the monitoring system and allow comparison across sentinel sites and against non-sentinel facilities in the same zone.

Client satisfaction assessments. A brief, five-item exit interview tool is administered to a purposive sample of 10–15 clients during each visit, capturing wait time experience, perceived completeness of the integrated care package, and overall satisfaction. Findings are recorded in the Visit Record module of the sentinel site form and triangulated with service delivery data to inform CQI action plans.

### Data analysis

The data will be analyzed descriptively and thematically based on the objectives, see table 1 in the data analysis plan.

Table 1: Analysis plan

| Objective | Priority indicators | Primary data sources | Analysis (simple) | Key outputs |
| --- | --- | --- | --- | --- |
| Objective 1: Identify and address system/process gaps affecting integrated service delivery | % tracer commodities available (priority list) | Sentinel Reporting Template, DHIS2/HMIS; Supervision Reports | Monthly/quarterly trend review; simple site scoring (red/amber/green); compare across sites/zones | Readiness & bottleneck scorecard; quarterly supervision/action completion brief |
|  | Stock-out days for key tracers |  |  |  |
|  | Referral/linkage functionality (yes/no or score) |  |  |  |
|  | DHIS2 reporting completeness/timeliness for agreed indicators |  |  |  |
|  | % supportive supervision actions closed (from action tracker) |  |  |  |
| Objective 2: Improve quality and performance of integrated service delivery through CQI and adaptive learning | # CQI mentorship visits conducted (per site/month) | Mentorship logs; CQI action plans; patient flow/time logs; service registers/DHIS2; learning logs & change package tracker, supervision reports | Before–after comparison for tested changes; cycle tracking; simple run charts; thematic synthesis of lessons | CQI progress summary; “what worked” briefs; change package toolkit + dissemination tracker |
|  | % priority CQI actions completed (per cycle) |  |  |  |
|  | Average client wait time (sampled) |  |  |  |
|  | % sentinel sites completing the integrated service package (agreed definition) |  |  |  |
|  | # validated changes packaged & disseminated (change packages/case notes) |  |  |  |

# Key outcomes

- Improved and sustained service outcomes and quality of care (better continuity, completion of the integrated package, and adherence to agreed SOPs/standards)

- Improved client experience and satisfaction (reduced waiting time, fewer visits, clearer pathways, and respectful, client-centred care)

- Improved service efficiency and system performance (streamlined patient flow, stronger referral/linkages, fewer stock-related disruptions, and better use of data for decisions)

## Resource considerations and budget

| - This budget only covers facilitation for the central and regional teams. - It does not cover site-specific inputs that maybe required to overcome bottlenecks to integration. SOPs, registers-digitization, Biometrics, majorly to be provided by government. - The validation visit will inform revision of the budget. - Establishing sentinel sites is front-loaded: it requires regional consultations, deployment of two national teams across all 16 regions, and initial site activation/documentation—hence per diem and transport costs for national and regional teams. - As functions are institutionalized, support shifts into routine RRH ICS and DHT work, with only periodic central input for complex issues and national learning synthesis. - Over time, this builds regional capacity and system learning, reducing dependence on central missions and improving integration efficiency and effectiveness across the health system |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Item | Quantity | Days | Per-diem | Total Perdiem | Milage | Fuel | Total |
| Central Team |  |  |  |  |  |  |  |
| Senior Officers | 3 | 6 | 175,000 | 3,150,000 | 1400 | 1,026,000 | 4,176,000 |
| Drivers | 2 | 6 | 175,000 | 2,100,000 |  |  | 2,100,000 |
| Supervisor CHS or ACHS | 1 | 6 | 175,000 | 1,050,000 | 1400 | 1,026,000 | 2,076,000 |
| Sub-total |  |  |  |  |  |  | 8,352,000 |
| Regional Team (ICS) |  |  |  |  |  |  |  |
| Executive Consultant | 1 | 3 | 175,000 | 525,000 | 500 | 366,429 | 891,429 |
| Regional TSS Team | 3 | 3 | 175,000 | 525,000 |  |  | 525,000 |
| Driver | 1 | 3 | 175,000 | 525,000 |  |  | 525,000 |
| Sub-total |  |  |  |  |  |  | 1,941,429 |
| Total for 1 Region |  |  |  |  |  |  | 10,293,429 |
| Total for 16 Regions | 16 |  |  |  |  |  | 164,694,864 |

### References

Bisset AL, Bhattarakosol P, Perera P, et al. Application of WHO’s guideline for the selection of sentinel sites for hospital-based influenza surveillance in Indonesia. BMC Health Services Research. 2014;14:424.

Gilson L, Barasa E, Nxumalo N, et al. Learning sites for health systems governance research: reflecting on our experience. Health Research Policy and Systems. 2020;18:54.

Guillot C, Bouchard C, Berthiaume P, et al. Criteria for selecting sentinel unit locations in a surveillance system for vector-borne disease: a decision tool. Frontiers in Public Health. 2022;10:1003949.

Palinkas LA, Horwitz SM, Green CA, et al. Purposeful sampling for qualitative data collection and analysis in mixed method implementation research. Administration and Policy in Mental Health. 2015;42(5):533–544.

Witter S, Namakula J, Ssengooba F, et al. Learning sites for health systems research: reflections on five programs in Africa, Asia, and Central America. Learning Health Systems. 2025. doi:10.1002/lrh2.10475.

World Health Organization. WHO Global Epidemiological Surveillance Standards for Influenza. Geneva: WHO; 2012. (Operational guidelines for sentinel SARI surveillance.)

Annex 1: Sentinel Site Data Collection Form

Ministry of Health Uganda — Integrated Service Delivery Learning & Adaptation Programme 2026–2027

Instructions: Use this form at every sentinel site visit. Module A is required at all visits. Module B (Site Profile) is completed at Activation only. Modules C–H are completed at all visits. Allow approximately 60 minutes per visit.

MODULE A: VISIT & SITE IDENTIFICATION   |   Complete at ALL visits

| Health Zone / RRH Region | District | Facility Name |
| --- | --- | --- |
| Facility Level | Ownership | Sentinel Site Code |

| Visit Type | Visit Date | Visit Number (follow-on) |
| --- | --- | --- |
| □ Activation (baseline) □ Follow-on visit |  |  |

| Lead Supervisor / Visitor (Name, Title, Organisation) | Team Members Present |
| --- | --- |
| Facility In-Charge Present | QI Focal Person Present |
| □ Yes □ No □ Partial visit | □ Yes □ No |

MODULE B: SITE PROFILE & BASELINE READINESS   |   Activation visit only

Complete at the activation visit to establish the validated baseline. Not required at follow-on visits.

B1. Staffing & Key Personnel

| Total staff on establishment | Staff present on day of visit | Critical vacant positions |
| --- | --- | --- |
| QI Focal Person designated? | QI Focal Person — Name & Contact |  |
| □ Yes □ No |  |  |

B2. Integration Enablers — Baseline Status   (Score: 0 = not in place  |  1 = partial  |  2 = fully functional)

| Enabler | Score (0–2) | Key gap / note |
| --- | --- | --- |
| Integrated registers / patient record system in use |  |  |
| One-stop integrated service point(s) established |  |  |
| Integrated appointments / scheduling system |  |  |
| SOPs and job aids for integration displayed and in use |  |  |
| Referral / linkage pathways documented and functional |  |  |
| DHIS2 / HMIS reporting complete and on time |  |  |
| Chronic care registers in use |  |  |
| Priority tracer commodities in stock (per checklist) |  |  |
| TOTAL SCORE (out of 16) |  | Last DHMT supervision score: _______% |

B3. Roles & Escalation — Agreed at Activation

Person responsible for site-level mentorship coordination (Name, title, contact)

Person responsible for implementation at facility (Name, title, contact)

Person responsible for documentation / learning logs (Name, title, contact)

Agreed escalation pathway for constraints (Facility → DHT → RRH ICS → MoH)

MODULE C: TRACER INDICATORS & READINESS CHECK   |   All visits

| Tracer Indicator | Value / Status | RAG (circle) | Note / Action needed |
| --- | --- | --- | --- |
| % priority tracer commodities in stock today |  | G A R |  |
| Stock-out days for key tracers (past 30 days) |  | G A R |  |
| Referral / linkage functionality (Functional / Partial / Non-functional) |  | G A R |  |
| DHIS2 reporting completeness (current month) |  | G A R |  |
| % prior supervision actions closed (from tracker) |  | G A R |  |
| Integrated service point operational today (Yes / Partial / No) |  | G A R |  |
| Average client wait time — sampled (minutes) |  | G A R |  |
| % clients completing full integrated service package (sampled) |  | G A R |  |
| Overall site readiness RAG this visit | □ GREEN □ AMBER □ RED |  |  |

MODULE D: CQI CYCLE PROGRESS (PDSA)   |   Follow-on visits

| # CQI mentorship visits this month | CQI Cycle Number |
| --- | --- |
| Change / intervention being tested this cycle (describe) |

| PLAN — What was planned | DO — What was done | STUDY — What data showed | ACT — Decision for next cycle |
| --- | --- | --- | --- |
|  |  |  | □ Adopt □ Adapt □ Abandon |

MODULE E: ACTION TRACKER   |   All visits

At follow-on visits, update status of prior actions before adding new ones.

| # | Action / Intervention | Responsible person | Due date | Status | Note |
| --- | --- | --- | --- | --- | --- |
| 1 |  |  |  | New / In progress / Done / Blocked |  |
| 2 |  |  |  | New / In progress / Done / Blocked |  |
| 3 |  |  |  | New / In progress / Done / Blocked |  |
| 4 |  |  |  | New / In progress / Done / Blocked |  |
| 5 |  |  |  | New / In progress / Done / Blocked |  |
| 6 |  |  |  | New / In progress / Done / Blocked |  |

MODULE F: LEARNING & ADAPTATION LOG   |   All visits

F1. What worked well this period? (cite specific changes and their effect)

F2. What did not work / key bottlenecks encountered?

F3. Key learning / insight from this visit (1–2 sentences)

| Does this learning warrant a change package / brief? | System issue requiring escalation to MoH? |
| --- | --- |
| □ Yes — document for dissemination □ Not yet | □ Yes — describe below □ No |
| If escalation needed — describe issue and recommended pathway |  |

MODULE G: CLIENT SATISFACTION — EXIT INTERVIEW SUMMARY   |   All visits

Administer the brief exit interview to 10–15 clients during the visit. Record aggregate findings below.

| # clients interviewed | % reporting wait time ≤ 60 mins | % received all expected services | % rating experience "good" or "very good" | % treated with respect |
| --- | --- | --- | --- | --- |
| Main client complaint / suggestion (most common theme from exit interviews) |

MODULE H: SIGN-OFF & NEXT VISIT   |   All visits

| Date of next planned visit | Priority focus for next visit |
| --- | --- |
| Immediate issues requiring action before next visit |

| Lead Supervisor Name & Signature | Facility In-Charge Name & Signature | QI Focal Person Name & Signature |
| --- | --- | --- |
| Date | Date | Date |

### Annex 1: List of the sites: Integration sentinels

| Zone | No | District | Facility | Level | Ownership |
| --- | --- | --- | --- | --- | --- |
| Arua RRH | 1 | Zombo_District | Paidha_HCIII | HCIII | GoU |
|  | 2 | Yumbe_District | Midigo_HCIV | HCIV | GoU |
|  | 3 | Nebbi_District | Nebbi_GH | Hospital | GoU |
|  | 4 | Maracha_District | St_Josephs_Maracha_Hospital | Hospital | PNFP |
|  | 5 | Arua_City | Arua_Regional_Referral_Hospital | RRH | GoU |
| Fort Port RRH | 1 | Fort_Portal_City | Kagote_HCIII | HCIII | GoU |
|  | 2 | Kabarole_District | Ruteete_HCIV | HCIV | GoU |
|  | 3 | Kyenjojo_District | Kyenjojo_GH | Hospital | GoU |
|  | 4 | Bunyangabu_District | Yerya_HCIII | HCIII | PNFP |
|  | 5 | Fort_Portal_City | Fort_Portal_RRH | RRH | GoU |
| Gulu RRH | 1 | Nwoya_District | Koch_Goma_HCIII | HCIII | GoU |
|  | 2 | Lamwo_District | Padibe_HCIV | HCIV | GoU |
|  | 3 | Kitgum_District | St_Josephs_Kitgum_Hospital | Hospital | PNFP |
|  | 4 | Nwoya_District | Anaka_GH | Hospital | GoU |
|  | 5 | Gulu_City | Gulu_Regional_Referral_Hospital | RRH | GoU |
| Hoima RRH | 1 | Kakumiro_District | Nalweyo_HCIII | HCIII | GoU |
|  | 2 | Masindi_District | Bwijanga_HCIV | HCIV | GoU |
|  | 3 | Kiryandongo_District | Kiryandongo_GH | Hospital | GoU |
|  | 4 | Kakumiro_District | St_Marys_Kakindo_HCIII | HCIV | PNFP |
|  | 5 | Hoima_City | Hoima_Regional_Referral_Hospital | RRH | GoU |
| Jinja RRH | 1 | Kaliro_District | Namwiwa_HCIII | HCIII | GoU |
|  | 2 | Iganga_District | Bugono_HCIV | HCIV | GoU |
|  | 3 | Iganga_District | Iganga_GH | Hospital | GoU |
|  | 4 | Iganga_District | Iganga_Islamic_Medical_HCIII | HCIII | PNFP |
|  | 5 | Jinja_City | Jinja_Regional_Referral_Hospital | RRH | GoU |
| Kabale RRH | 1 | Rukungiri_District | Nyarushanje_HCIII | HCIII | GoU |
|  | 2 | Kanungu_District | Kanungu_HCIV | HCIV | GoU |
|  | 3 | Kisoro_District | Kisoro_GH | Hospital | GoU |
|  | 4 | Kabale_District | Rugarama_Hospital | Hospital | PNFP |
|  | 5 | Kabale_District | Kabale_Regional_Referral_Hosp | RRH | GoU |
| Kayunga RRH | 1 | Kayunga_District | Nazigo_HCIII | HCIII | GoU |
|  | 2 | Mukono_District | Kyetume_CBHC_HCIV | HCIV | PNFP |
|  | 3 | Buikwe_District | Ngogwe_HCIII | HCIV | GoU |
|  | 4 | Mukono_District | Mukono_COU_Hospital | Hospital | PNFP |
|  | 5 | Kayunga_District | Kayunga_Regional_Referral | RRH | GoU |
| Lira RRH | 1 | Apac_District | Ibuje_HCIII | HCIII | GoU |
|  | 2 | Kwania_District | Aduku_HCIV | HCIV | GoU |
|  | 3 | Apac_District | Apac_GH | Hospital | GoU |
|  | 4 | Lira_City | Lira_University_Hospital | Hospital | PNFP |
|  | 5 | Lira_City | Lira_Regional_Referral_Hospital | RRH | GoU |
| Masaka RRH | 1 | Lyantonde_District | Mpumudde_HCIII | HCIII | GoU |
|  | 2 | Wakiso_District | Kabubbu_HCIV | HCIV | PFP |
|  | 3 | Lyantonde_District | Lyantonde_GH | Hospital | GoU |
|  | 4 | Kyotera_District | St_Andrews_Bkira_Maria_HCIV | HCIV | PNFP |
|  | 5 | Masaka_City | Masaka_Regional_Referral_Hosp | RRH | GoU |
| Mbale RRH | 1 | Namisindwa_District | Bupoto_HCIII | HCIV | GoU |
|  | 2 | Mbale_City | Bufumbo_HCIV | HCIV | GoU |
|  | 3 | Bududa_District | Bududa_GH | Hospital | GoU |
|  | 4 | Bukwo_District | Bukwo_HCIV | HCIV | PNFP |
|  | 5 | Mbale_City | Mbale_Regional_Referral_Hospital | RRH | GoU |
| Ankole | 1 | Buhweju_District | Karungu_Buhweju_HCIII | HCIII | GoU |
|  | 2 | Rubirizi_District | Rugazi_HCIV | HCIV | GoU |
|  | 3 | Sheema_District | Kitagata_GH | Hospital | GoU |
|  | 4 | Kiruhura_District | Rushere_Community_Hospital | Hospital | PNFP |
|  | 5 | Mbarara_City | Mbarara_Regional_Referral | RRH | GoU |
| Moroto RRH | 1 | Kotido_District | Rengen_HCIII | HCIII | GoU |
|  | 2 | Nakapiripirit_District | Tokora_HCIV | HCIV | GoU |
|  | 3 | Kaabong_District | Kaabong_GH | Hospital | GoU |
|  | 4 | Napak_District | St_Kizito_Matany_Hospital | Hospital | PNFP |
|  | 5 | Moroto_District | Moroto_Regional_Referral_Hosp | RRH | GoU |
| Mubende RRH | 1 | Mubende_District | Mubende_Kasambya_HCIII | HCIII | GoU |
|  | 2 | Kassanda_District | Kassanda_HCIV | HCIV | GoU |
|  | 3 | Mityana_District | Mityana_GH | Hospital | GoU |
|  | 4 | Mityana_District | St_Francis_Mityana_HCIV | HCIV | PNFP |
|  | 5 | Mubende_District | Mubende_Regional_Referral | RRH | GoU |
| Entebbe RRH | 1 | Wakiso_District | Kigungu_HCIII | HCIII | GoU |
|  | 2 | Wakiso_District | Kabubbu_HCIV | HCIV | PNFP |
|  | 3 | Nakaseke_District | Nakaseke_GH | Hospital | GoU |
|  | 4 | Mpigi_District | Nkozi_Hospital | Hospital | PNFP |
|  | 5 | Wakiso_District | Entebbe_Regional_Referral | RRH | GoU |
| Soroti RRH | 1 | Bukedea_District | Malera_HCIII | HCIII | GoU |
|  | 2 | Kapelebyong_District | Kapelebyong_HCIV | HCIV | GoU |
|  | 3 | Kumi_District | Atutur_GH | Hospital | GoU |
|  | 4 | Serere_District | Kidetok_Mission_HCIII | HCIII | PNFP |
|  | 5 | Soroti_City | Soroti_Regional_Referral_Hosp | RRH | GoU |
| Yumbe RRH | 1 | Obongi_District | Palorinya_HCIII | HCIII | GoU |
|  | 2 | Adjumani_District | Mungula_HCIV | HCIV | GoU |
|  | 3 | Moyo_District | Moyo_GH | Hospital | GoU |
|  | 4 | Koboko District | Koboko Mission Health Centre III | HC III | PNFP |
|  | 5 | Yumbe_District | Yumbe_Regional_Referral_Hospital | RRH | GoU |

### Annex 2: Roles

| Level | Core Role | Key Responsibilities |
| --- | --- | --- |
| MoH Central Team | National stewardship, policy alignment, and learning synthesis | - Define national learning agenda and integration priorities - Develop/standardize tools, SOPs, indicators, and learning templates - Lead sentinel site selection approval and regional activation - Provide high-level technical guidance and resolve system-level bottlenecks - Synthesize lessons and translate into policy, guidelines, and training updates - Support QI approaches at sentinel sites - Mobilize resources and coordinate partners Convene national learning and review forums |
| RRH Integrated Care System (ICS) Team | Regional stewardship and technical coordination | - Serve as regional entry point for sentinel implementation - Coordinate activation visits and ongoing mentorship - Support facilities to operationalize integration workflows and SOPs - Lead regional peer learning exchanges - Monitor indicator performance and support data use - Escalate system constraints to MoH central team - Support spread of successful practices to non-sentinel facilities |
| District Health Teams (DHMTs) | Routine supervision, follow-up, and spread | - Conduct routine supportive supervision and follow-up on action plans - Support facility teams to implement integration improvements - Monitor performance and ensure data reporting completeness - Facilitate adoption of tested practices in non-sentinel facilities - Coordinate local problem-solving and resource alignment - Engage local leadership and PNFP partners |
| Facility (Sentinel Site) Teams | Implementation, quality improvement, and learning generation | - Establish/strengthen integration/QI team and focal person - Implement integration SOPs and workflow improvements - Conduct regular QI cycles (PDSA) and document results - Maintain learning logs and share lessons - Monitor indicators and hold monthly data review meetings - Host peer learning visits and demonstrate practices - Escalate operational barriers through DHMT/RRH ICS |