## Slide 1
UGANDA MINISTRY OF HEALTH • HEALTH SERVICE INTEGRATION
Sentinel Learning &
Adaptation Sites
for Integrated Service Delivery
Activation • Assessment • CQI • Learning
80
sentinel sites
16
health zones
5
sites per zone
36
months of learning
Regional / District / Facility Orientation • September 2026

## Slide 2
THE PROBLEM
Why Sentinel Learning Sites?
✓
Policy direction is clear
The National Integration Framework and related guidance provide the direction for integrated service delivery.
!
Implementation is uneven
Facilities and districts are at different stages. Patient flow, referrals, documentation, commodities and data use are not yet consistent.
?
We need to know what works
We need a systematic way to learn what drives integration at different levels of care—and how effective practices can be adapted and spread.
Sentinel Learning Sites provide a structured mechanism to learn, improve and spread what works.

## Slide 3
A PRACTICAL LEARNING HUB
What is a Sentinel Learning Site?
01
CQI engine
Teams identify priority gaps, test small changes through PDSA cycles, review data and document what improves care.
02
Demonstration hub
Sites show nearby facilities at the same level of care what integrated service delivery can look like in routine practice.
03
Learning generator
Sites produce practical lessons, learning briefs and change packages that can be shared through district, RRH and national structures.
How learning spreads
Sentinel site
CQI cycle
Change package
documented
DHMT
supervision
RRH / regional
peer learning
MoH
guidance
Not a research site. Not a survey. Not a performance award. A structured learning and improvement site.

## Slide 4
METHODOLOGY
The Network: Stratified Random Selection
District-level randomisation is complete. Facility selection now proceeds through verified stratified random selection.
80
total sites
16
health zones
5
sites per zone
0
eligibility screens
1
20 JULY
Districts randomised
Districts completed a preliminary randomisation exercise, establishing the pathway for facility selection.
2
Compiled facility frame
Verified facility lists by district/zone, level of care and ownership.
3
Stratification
Grouped facilities by level of care — RRH/Hospital, HC IV, HC III — and by GoU/PNFP ownership.
4
Randomised within strata
Used a lottery or Excel RAND so selection was not driven by convenience or preference.
5
Validated & activate
Confirmed factual details and operational readiness, plan to initiate baseline assessment and action planning.
PER-ZONE TARGET COMPOSITION
2× HC III
2× HC IV
1× RRH / Hospital
PNFP representation is captured within the ownership strata.

## Slide 5
The full sentinel site cycle
It is SOPs + staging + inputs + action tracker + QI + learning.
11
1. Use SOPs
Put the SOPs into daily practice at service points.
2. Stage
Assess current maturity across integration domains.
3. Identify inputs
Document tools, commodities, HRH, space, data and support gaps.
4. Track actions
Agree owners, dates, support needs and status.
5. Run QI
Use PDSA cycles to test improvements and review data.
6. Share learning
Document what worked and spread it through DHMT/RRH forums.
Ministry of Health Uganda Health Facility Orientation Sentinel Sites & SOPs August 2026

## Slide 6
The Assessment Tool builds on existing tool
One tool. One visit. Action plan before the team leaves.
D1
Leadership
& Governance
D2
Service
Delivery ★
D3
Commodity
Management
D4
Health
Information
D5
Human
Resources
D6
Laboratory
Systems
D7
Community
Systems
D8
Health
Financing
D9
Quality
of Care
Each domain tab contains:
A. Staging
Score 1–5 for each standard. Score turns Red→Green automatically.
B. Key Indicators
Pre-filled baselines and targets from the national M&E framework.
C. Synthesis & Action Plan
Up to 5 gaps → intervention type → responsible person → timeline.
E. Shared Experiences
What worked, what changed, what can other sites replicate?
Each domain includes Staging (1–5, traffic-light colours), KPIs pre-populated from the M&E Framework, a Synthesis & Action Plan (top 5 gaps), and Shared Experiences by standard — auto-linked to the Action Tracker. Plus: Client Satisfaction · Action Tracker · Dashboard · Data Extraction.
Notes: Every domain should end with priority gaps translated into actions, owners and timelines—not scores alone.

## Slide 7
HOW SCORING WORKS
Each standard is scored 1 to 5. The colour tells the story instantly.
1
No integration (20%)
Services remain vertical. No coordination or shared pathways between programmes. Patients visit each service point separately.
2
Minimal alignment (40%)
Isolated steps exist — ad hoc and unsustained. Some staff are doing integrated care but it is not systematic or documented.
3
Partial integration (60%)
Some structure is visible — SOPs exist, some staff follow integrated pathways — but practice is uneven across staff and service points.
4
Strong alignment (80%)
Integration is routine and documented. Most staff follow integrated protocols consistently. The facility is sustaining integration independently.
★ Our target is Score 4
Score 4 = 80% = Strong Alignment
✓ Integrated protocols are in use
✓ Most staff follow integration SOPs
✓ CQI is active and documented
✓ Data is reviewed and used
✓ Referrals are tracked and completed
If your facility is at 3 — we work together to reach 4. If you are at 4 — we work toward 5.
5
Full integration (100%)
Comprehensive, patient-centred integrated care is consistently demonstrated and self-sustaining. The facility can mentor other sites.
Notes: MATURITY SCALE—NOT A PASS/FAIL SCORE

## Slide 8
INPUTS • ACTION TRACKER • FOLLOW-UP
From findings to action
1
1. Check the enabling inputs
People
Tools and registers
Commodities
Space and patient flow
Data systems
Mentorship support
2
2. Agree the action tracker
Priority gap
Agreed action
Owner
Due date
Support needed
Status
3
3. Follow up and escalate
Review monthly
Use routine data
Escalate system bottlenecks
Document learning
Update status
No visit should end with observations only. It should end with agreed actions and a clear route for escalation.

## Slide 9
QI is part of the process
QI helps the facility solve the problems identified through staging and the action tracker.
15
Problem
Choose one priority gap from the tracker.
→
Root cause
Ask why the gap is happening.
→
Change idea
Agree one small change to test.
→
PDSA cycle
Plan, do, study and act.
→
Data review
Check whether the change improved results.
QI is how the facility turns the action tracker into improvement.
Ministry of Health Uganda Health Facility Orientation Sentinel Sites & SOPs August 2026
QI is not needed for every gap. Use it for priority problems where a practical change can be tested, measured and refined.

## Slide 10
CLEAR OWNERSHIP AT EVERY LEVEL
Roles, reporting and escalation
Facility team
Use SOPs • run CQI/PDSA • maintain learning logs • review data monthly
DHMT
Routine supervision • follow up action plans • solve local bottlenecks • spread tested practice
RRH / regional ICS
Activation • mentorship • peer learning • data use • escalation of system constraints
MoH / NACI
Stewardship • standard tools/SOPs • national synthesis • policy uptake • unblock decisions
Reporting pathway: Facility → DHMT → RRH/Regional ICS → MoH/NACI, with learning and unresolved bottlenecks escalated upward.

## Slide 11
Facility roles and accountabilities- SOPs
Everyone has a role, but coordination must be clear.
16
Facility in-charge
Overall accountability, staff orientation and escalation.
SOP / integration focal person
Coordinates SOP placement, tracking and learning logs.
Service-point teams
Use SOPs and identify
practical barriers.
QI team
Runs root-cause analysis and PDSA cycles.
Records/data team
Supports data extraction and monthly reviews.
DHMT / RRH mentors
Provide mentorship, validation and escalation support.
Ministry of Health Uganda Health Facility Orientation Sentinel Sites & SOPs August 2026

## Slide 12
WHERE WE ARE NOW
Implementation timeline
Mar–Aug 2026
Foundation
Site selection
Assessment tool finalised
SOPs developed
Teams prepared
Sep–Oct 2026
Activation
Baseline assessments
First mentorship visits
CQI cycles initiated
First learning synthesis
WE ARE HERE
Nov–Dec 2026
Review & refine
Performance review
Second mentorship/CQI round
Change packages documented
2027–2028
Scale learning
Repeated learning cycles
National synthesis
Change package toolkit
Guidance updates
The September visit establishes the baseline and first actions; subsequent visits should follow progress rather than start again.

## Slide 13
FIVE PRACTICAL ACTIONS
What should happen during the first activation visit?
1
Confirm the facility focal person and core team
Agree who will support staging, QI, records and service-point follow-up.
2
Place SOPs where care happens
Use printed/digital SOPs at registration, triage, consultation, laboratory, pharmacy, exit and community follow-up.
3
Complete staging and inputs review
Agree the facility starting point across the nine domains and identify missing inputs.
4
Agree the action tracker before the team leaves
Convert priority gaps into actions, owners, dates, support needs and escalation points.
5
Start the first QI focus and capture learning
Pick a priority problem, test a practical change, review data and document what is learned.
The main message
No visit should end with observations only.
It should end with an agreed action tracker, an initial QI focus, and a clear follow-up plan.
Facility teams own the process. Mentorship teams support, validate and help escalate what the facility cannot solve alone.
Use the SOPs • stage the facility • track actions • run QI • share learning.

## Slide 14
THANK YOU
Questions & Discussion
Ministry of Health, Uganda
Integration Reform Workstream
Email: sopfeedback@gmail.com