[MINISTRY OF HEALTH SENTINEL SITE ACTIVATION SCHEDULE
6-12 SEPTEMBER 2026

| Time | Monday Entry for RRH | Tuesday Sentinel Site | Wednesday Sentinel Site | Thursday Sentinel Site | Friday |
| --- | --- | --- | --- | --- | --- |
| 08:00-10:00 Morning | Regional entry - Introducing the week’s programme. - Objectives and Introductory Presentations to RRH Leadership | Presentations to DHT Leadership/District - Introducing the week’s programme. - Objectives and Introductory Presentations to RRH Leadership | - Elaborate CQI Session. Propose a CQI Project; - Use of SoPs | - Completion of Mentorship Tool- Learning. - Completion of Mentorship Tool- Synthesis and Action Plan. | - Key findings. - Action Planning. - Close out. |
| 11:00-13:00 |  | Presentations to Facility Team. - About Integrated Delivery of Health Services & The Sentinel Site Intervention. Target Audience: All Health Workers |  |  |  |
| 13:00-14:00 Lunch | Lunch | Lunch | Lunch | Lunch |  |
| 14:00-15:00 | Team Review - Constitute the Final Mentorships team and IPS - Allocate Teams to all the Sentinel Sites - Confirm readiness, roles and Tuesday assessment tasks | - Completion of Mentorship Tool- - Staging - Completion of Mentorship Tool- Key Performance Indicators | - SOPs Presentation |  |  |
| 16:00-16:30 Daily review | - Teams Dispatched to other Sentinel Site |  | Team Review |  |  |

DELIVERABLES PER FACILITY: 

By the time you leave the facility, the following should have been achieved;

- Orientation on Sentinel Sites Concept, CQI, SOPs (including presentation of each SOP overview) and Facility Staging.

- Data collection using the Site Staging/Assessment Tool

- At least one CQI project started

- Development of the written follow-up Action Plan